## Sheet1
Timeline
Date | Frontend | Backend
1st week | Requirement gathering | creating ERD
2nd week | login/signup, homePage | api for login/signup, homepage
3rd week | product Page | api for product page
4th week
5th week
6th week
Date | 17th january 2023
1 | Requirement gathering
2 | installation of required app | react in frontend and django in backend
3 | database design | erd
Requirement gathering
app function:
view product categories
view second hand items
view best items
view new arrival
Date | 2023-01-23
1 | learn how to create component in React
2 | learn how to create api in django
3 | learned about response, serialization and CRUD operation
Date | 2023-01-24
1 | learn how to use and implement routing in React
2 | sign up page was created
3 | learn rest framework documentation in django